| The Presidency |  | Federal Ministry of Budget and National Planning of Nigeria |  |
| --- | --- | --- | --- |

Terms of References

Independent Evaluation of the Effectiveness & Impact of the Sustainable Development Goal

(SDG-4 Education) in Nigeria

Abuja, 19 June 2019

Table of contents

Page

1.	Context and Object of the Evaluation	4

1.1.	Country situation	4

1.2.	Evaluation object	5

1.2.1. Expected Results of the Education Sector Strategic Plan 2016-2019	6

1.2.2. Theory of Change (ToC) of Education Sector Strategic Plan 2016-2019	7

2.	Purpose of the Evaluation	8

3.	Evaluation Objectives	10

4.	Scope of the Evaluation	10

4.1.	Thematic scope	10

4.2. Geographic Scope	11

4.3.Periodic Scope	11

5.	Evaluation Criteria and Questions	12

5.1.	Evaluation Criteria	12

5.2.	Evaluation Questions per Criteria	12

6.	Methodology of the Evaluation	14

6.1.	Overview of the Evaluation Design	14

6.2.	Recap of available evidence	14

6.3.	Quasi Experimental Design	15

6.4.	Qualitative methods	19

6.5.	Other methodological considerations	19

6.6.	Data Processing & Analysis	20

6.6.1.	Quantitative data analysis	20

6.6.2.	Data Entry, Management and Quality Assurance of HH survey	20

6.6.3.	Quality Assurance of data collection for field studies	21

7.	SDGs Evaluation Governance & Quality Assurance	21

7.1.	National Steering Committee (NSC) on SDGs Evaluation	21

7.2.	Technical Working Group of SDGs Evaluation in Nigeria	22

7.3.	Timely Management of the Evaluation	23

7.4.	Independent Evaluation Consulting Firm Team	24

7.5.	Oversight Quality Assurance of SDGs Evaluation	24

8.	Evaluation Expected Deliverables-Outputs	25

9.	Evaluation workplan	26

10.	Ethical Considerations	27

11.	Evaluation Team and responsibilities	28

11.1.	Evaluation Team Leader: International	28

11.2.	Other Members of the Team	29

12.	Competitive Contracting Bidding Process	29

Annexes	31

A1. Evaluation Framework: link between Criteria, Questions and Data Sources	31

A2. References & Bibliographies	31

# Context and Object of the Evaluation

## Country situation

The achievement of the 2030 Agenda for Sustainable Development so as to ‘leave no one is behind’, is an important global commitment for United Nations member states and development partners. Nigeria is the most populous country in Africa – with approximately 180 million people, as well as the largest economy in Africa – with 2018 Gross Domestic Product (GDP) estimated at N136 trillion. Its governance structure comprises of a Federal Government, 36 state and the Federal Capital Territory and 774 Local Government Areas (LGAs). Nigeria’s Arms of government include the Executive, Legislature and the Judiciary.

The Nigeria’s National Policy on Education (2004) has been a major step in increasing access to basic education in Nigeria, by making basic education ‘free and compulsory’. Nevertheless, at least 10 million children are reported to be ‘out of school’ in Nigeria. With approximately 20 million Out-of-school children globally, Nigeria has the highest number of out-of-school children in the world. Only 61% of 6-11-year olds regularly attend primary school and only 36 per cent of children between three and five attend organized early childhood education programmes (MICS, 2016). Regarding the quality of education, about ‘50% of in-school children are not learning as expected’, and therefore cannot read or write. That approximately 63% of children who live in rural areas cannot read at all; and around 84% of children in the lowest economic quartile cannot read at all’ (ibid).

The Federal Government collaborates with sub-national governments and the private sector in implementing the Education Strategic Plan (2016-2019) entitled ‘Education for Change’. The Plan aimed at improving access and quality to education across the country. Implementation of the strategies in the Plan is expected to inspire schools to design and implement teacher training programmes, comprising peer reviews through classroom visits, collaborative lesson planning and weekly sessions.

The implementation of the provisions of the Education Sector Strategic Plan starts from Primary through Secondary school levels. This includes the overhaul and review of the ICT curriculum, which comprises of Computer Science, Information Technology and Digital Literacy. This is envisaged to be jointly carried out with relevant education stakeholders in order to ensure appropriate and adaptive programme objectives. Tracking of progress and performance, as well as facilitating effective intervention and integration of lessons learned are key. In addition, the government plans to prioritize Girl-Child education and Almajiri education through the construction of ‘Special schools’.

## Evaluation object

This Independent SDG evaluation will focus on SDG-4, which aims to ‘ensure inclusive and quality education and promote lifelong learning opportunities for all’ in Nigeria by 2030. During the SDG Evaluation Capacity Building Workshop held in Lagos between February 4th and 8th, 2019, on SDG evaluation capacity building, participants from the OSSAP-SDGs, the MBNP, relevant Ministries, Departments and Agencies (MDAs), United Nations Agencies, development partners, Academia and the CSOs agreed to prioritize SDG-4. Thus, SDG-4.1 is considered as the main focus of this independent evaluation:

- By 2030, ensure that all girls and boys complete free, equitable and quality primary and secondary education leading to relevant and effective learning outcomes.

Nigeria has developed and operationalized a Medium-Term National Development Plan, tagged the ‘Economic Recovery and Growth Plan (ERGP 2017-2020)’. The ERGP aims to restore economic growth, invest in people, and build a globally competitive economy. The economic, social and environmental dimensions of the SDGs have been mainstreamed into the ERGP 2017-2020. Specific to the Nigerian Education Sector, the government has developed and implemented the ‘Education for Change’ Strategic Plan 2016-2019, which is built on the strategic intent of the Universal Basic Education Act (2004). The Education Sector Strategic Plan has integrated SDG-4, with the aim of achieving ‘Universal access and quality in primary and secondary education for all’.

Figure 1 shows the challenging decreasing trend in access to Primary Education up till 2016, taking into account the 2016 economic recession and continuous demographic burden.

Figure 1: Nigeria’s Trend in Net Enrollment Ratio in Primary School

Intended long term impact of the 2016-2019 Education Sector Strategic Plan was to create ‘a real and positive change that will reposition the sector and make positive difference to the lives of the citizens and to the prosperity and competitiveness of the nation’. The Strategic Plan contains 10 pillars as follows:

- Addressing the out-of-school children phenomenon;

- Strengthening basic and secondary school education;

- Teacher education, capacity building and professional development: Training of 500,000 Teachers;

- Adult literacy and special needs education;

- Education data and planning;

- Curriculum and benchmark minimum academic standard;

- Technical and vocational education and training;

- Quality and access in higher education;

- Information and Communication Technologies (ICT)

in Education; and.

- Library Services in Education

Flagship programmes and public-private investment have been promoted like Conditional Cash Transfer Initiatives, the Home-grown school feeding programme and the Female Teachers Trainee Scholarship Scheme (FTTSS) that aim to address inequity issues and reinforce access and retention to school.

Four years after the implementation of the sector strategic plan in mainstreaming SDG-4, the Ministry of Education is committed to developing a new Education Sector Strategic Plan for the next three years (2020-2022). This independent evaluation of SDG-4 will focus on assessing the merit of results achieved in Nigeria vis-à-vis SDG-4, which ensures ‘inclusive and equitable quality education and promotes life-long learning opportunities for all’ within the ERGP 2017-2020, the Education for Change Strategic Plan 2016-2019 and UBE Act 2004.

The object of this evaluation is to assess objectively the effectiveness and impact of the four-year ‘Education Strategic Plan 2016-2019’ in contributing to achieve SDG-4.1 in Nigeria. This is aimed at in-depths explanations of success or probable shortfalls that will serve as learning for adequate solutions. In-depth evidence will be generated for better learning of what worked in education sector and what didn’t work? Why? and what are the key drivers that Government and development partners can act on?

Evidence generated from this in-depth and objective assessment will be used by Government/Ministry of Education and Education Sector Development Partners Group to formulate better strategies and prioritize public investment for accelerating progress towards achieving SDG-4 in Nigeria.

1.2.1. Expected Results of the Education Sector Strategic Plan 2016-2019

In the absence of Results Based Planning approach, the Education Sector Strategic Plan 2016-2019 contain several Table of Action Plans built around the 10 pillars mentioned above, using the activity-based approach for planning. We try to identify and prioritize high level expected results for each section in order to figure out result framework of impact and outcomes required for the SDG-4 evaluation.

Table 1: Results Framework (impact and outcomes) constructed using the table of Action Plan of the Education Strategic Plan 2016-2019.

| Pillar | Strategic Objective | Expected results in 2019 |
| --- | --- | --- |
| 1.Out of school Children | Ensure that all of out of school children are enrolled in basic education schools in the next four years | Enroll 2,875,000 pupils annually for the next four years; |
|  |  | Raise the current enrolment of girls in basic education schools by 1.5 million girls annually |
|  |  | Raise the current enrolment in Nomadic schools from the present 17% to 30-40% |
|  |  | Construct and furnish additional 71,875 classrooms annually for the next four years to accommodate the anticipated increase in enrolment; |
|  |  | Recruit additional 500,000 qualified teachers (promised by the Federal Government) in tranches, to cater for the anticipated increase in pupils’ enrolment; |
|  |  | Recruit 37,500 qualified female teachers, (or 7.5% of the new teachers promised by federal government) annually |
|  |  | Implement school feeding programme |
|  |  | Reactivate the initiative on the out-of-school boy-child syndrome in the South East and South-South geo-political zones which was inexplicably abandoned in 2014 |
| 2.Basic Education | Net Enrollment ratio is increased to 100 % (engagement to Universal Education 2015) | All (100%) children of primary school age (girls as well as boys) will be enrolled in primary school or its equivalent. |
|  |  | Completion rate is improved by 30% to an overall rate exceeding 90% of those in schools |
|  |  | 50% increase in the number of children with disabilities mainstreamed into primary school |
|  |  | Transition rate from primary to junior secondary school reach 90%. |
|  |  | 80% of children up to the age of 15 will be enrolled in school or an equivalent education programme |

1.2.2. Theory of Change (ToC) of Education Sector Strategic Plan 2016-2019

The Education Sector Strategic Plan 2016-2019 doesn’t have a Theory of Changes (ToC). Thus, in the absence of a ToC, the Independent Evaluation Team will be expected to re-construct a ToC as an entry point of the entry point of the evaluation. For the purpose of providing a broader picture of the desired changes of the Four (4) years of the education sector (object of the evaluation), we drafted below diagram using information from the Actions Plan.

Figure 2: Draft0 incomplete Theory of Changes (ToC) of the Education Sector Strategic Plan 2016-2019 - with focus on SDG-4.1 on Out of School Children and Basic Education

Desire Changes: Achieve SDG4-Target1 of 100 % Completion Rate by 2030 – Zero children are out of school

Impact: By 2030, All girls and boys complete free, equitable and quality primary education leading to relevant and effective learning outcomes

Outcome 1: All of out of school children are enrolled in basic education schools in the next four years

Outcome2: All (100%) children of primary school age (girls/boys) will be enrolled in primary school or its equivalent

Output 1.1: Enroll 2,875,000 pupils annually

Output 1.2: Additional 71,875 classrooms are constructed annually

Output 2.1: Access: 80% of children up to the age of 15 will be enrolled in school or an equivalent education programme

Output 2.2: Improved Quality of primary education

Output 1.3: Recruit additional 500,000 Teachers in 4 years

- Enabling Environment: Governance, Budget, Policies, Nigeria education management information system (NEMIS), Information, Communication and Technology

- Supply & Coverage: Geographic access/infrastructures, Library Service in Education, School Materials,

- Demand: Social Norms and family behaviors, School Cost/Fees, School feeding, etc…

- Quality: Basic and secondary education Curricula, Pre-service Teacher Education, WASH conditions and child protection in school

Problem: Low Completion Rate (63%) - at least 10 million children are out of primary school

# Purpose of the Evaluation

The Independent Evaluation of SDG-4 on ‘ensuring inclusive and equitable quality education and promotes life-long learning opportunities for all’ was commissioned by government of Nigeria, through the Office of the Senior Special Assistant to the President on SDGs (OSSAP-SDGs) for the purpose of i) learning, ii) accountability and iii) evidence-based Voluntary National Review in 2020. Federal and state governments, Development actors and key stakeholders would like to know what is working well and how? What didn’t work and why? Key findings would be used to fast-track and accelerate progress in the next 11 years of the 2030 Agenda for sustainable development and the SDGs.

- Learning:

The independent evaluation is expected to assist the government (national, state and Local) and other key stakeholders in developing and improving the implementation modalities of the new Education Strategic Plan 2020-2022 for the acceleration of progress towards achieving SDG-4. It will provide in-depth understanding of the key drivers of success and challenges to achieving the strategic objectives of the Education Sector Plan.

- Accountability:

This independent evaluation will provide sound evidence on whether the implementation of the Education Strategic Plan has contributed to achieving SDG-4.

- SDGs Voluntary National Review 2020:

The key findings of this independent evaluation will be used to strengthen evidenced-based Nigeria’s SDGs Voluntary National Review Report in 2020. This is expected to enhance credible participation of Nigeria during strategic debate and to influencing global vision at the UN High-Level Political Forum on Sustainable Development in 2020.

Table 2: Evaluation Users and Uses

| Evaluation Users | Evaluation Uses |
| --- | --- |
| Presidency – Office of the Senior Special Assistant to the President on SDGs | - To inform the President about success and challenges of SDG-4 and their explanations for adequate evidence-based policy decision making (1-page summary); - Organize National Forum of strategic debate of lessons learned and required corrective measures; - To integrate findings and lessons learned into Nigeria NVR 2020 and influence global policy advocacy at UN High Level Political Forum in New York. - To lead on adequate policy decision/responses to conclusions and recommendations of the evaluation through the adoption and operationalization of acceleration strategies & actions; - To lead on bi-annual follow up Management Responses of Planned Actions; |
| Ministry of Education | - To ensure adequate evidence-based development of the forthcoming Education Sector Strategic Plan 2020-2022 using lessons learned from this independent SDG-4 evaluation. - Evidence-based public advocacy to leverage large scale public-private partnerships and adequate investment to Education Sector; - To scale up innovative strategies and approaches revealed by the evaluation and accelerate progress towards SDG-4. |
| Ministry of Budget and National Planning | To ensure adequate evidence-based National Budget Planning for Education Sector; adopt rigorous method of use of Theory of Changes for deliberations on budget. |
| Ministry of Finance | Use evidence for adequate budget allocation and expenditures to Education Sector and funding of Education Flagship programmes |
| Parliament | To ensure appropriate budget review/allocation to Education Sector and follow up of Nigeria’s progress to meet country’s engagement for SDGs |
| Other MDAs | To mainstream the improved Strategies and implementation modalities (see above) of SDG-4 into the relevant sections of their respective sectoral plans to achieve agenda 2030. |
| State Ministries of Education | - To develop, fund and implement the new Education Strategic Plan 2020-2022; - To introduce more innovative SDG-4 interventions as part of acceleration strategy. |
| Development Partners | - To inform their future allocation of resources (Technical and financial) to SDG-4 related areas of intervention - Realignment of programme support and accountability |
| Nigerian Association of Evaluators (NAE) | - Follow up on evaluation findings and recommendations; advocacy |
| CSOs | - To strengthen Sensitization amongst communities on the value of education against the negative vices of child labor and early marriages. - To strengthen Advocacy to authorities towards enforcement of existing SGD 4 friendly policies and formulation of new policies - To strengthen advocacy within the CSO and donors towards judicious use of funds |
| Private Sectors | To inform Resource mobilization and Corporate Social Responsibility strategies in SDG 4 related intervention |

# Evaluation Objectives

Specific objectives of this independent evaluation are to:

- Measure the extent to which the Education Sector Strategic Plan (2016-2019) has been effectively implemented with regards to the provision of access, equity and quality basic education for girls and boys.

- Assess the level of completion for girls and boys at basic education.

- Determine the extent to which effective learning outcomes have been achieved.

- Understand the driving factors (explanations), strengths and weaknesses (bottlenecks) in the implementation of selected strategic Education programmes.

- Provide strategic recommendations that will help identified evaluation users, such as national and sub-national governments, development partners and non-state actors to accelerate progress and achieve SDG-4 in Nigeria.

# Scope of the Evaluation

## Thematic scope

Three major thematic areas of the basic education will be covered by this evaluation:

- The evaluation will measure the level of access (and the lack thereof) to primary and basic education nationwide, as well as the quality of teaching and learning.

- The evaluation will highlight the link between SDG-4 and other related SDGs (e.g. SDGs 2, 6 and 8), gender issues and skills acquisition.

- The evaluation will also look at the dimension of gender access, equity and Human rights.

## 4.2. Geographic Scope

This evaluation will cover all the 36 states and FCT.

Figure 3: Map of Nigeria showing 36 states and the FCT

## 4.3.Periodic Scope

This evaluation will cover SDG-4, target-1 related interventions, implemented between September 2015 and June 2019. The Evaluation will cover the period from 2016 to 2019 (4 years). However, a long-term 10-year period will be considered for the trend & causal analysis of impact indicators of SDG-4 target 1.

Figure 4: Trend & causal analysis of Universal Access & Quality

Completion Rate

SDG Target = 100%

What worked, what didn’t Work and Why?   To increase Access, Quality & Completion

CR = 63%

2010

2015

VNR 2020

2025

2030

# Evaluation Criteria and Questions

## Evaluation Criteria

The evaluation will assess the Relevance, Impact, Effectiveness, Efficiency and Sustainability of the Education Sector Strategic Plan 2016-2019 in contributing to the achievement of SDG-4.1 in Nigeria. These criteria are well aligned to the Five (5) universal OECD DAC standard criteria for evaluating development assistance and are defined in Table 3. Five other ‘cross cutting’ criteria linked to SDG Principles are added, namely, Universality, Equity, Human Rights, ‘Leave no one behind’ and Gender sensitivity. For each criterion, the judgement of the merit of the Education Sector Strategic Plan 2016-2019 in contributing to the achievement of SDG-4.1 will be performed using specific quantitative indicators. This is in addition to qualitative data collection and analysis of beneficiaries and stakeholders. Details of indicators for the measurement of each universal criterion/principles for SDGs evaluation will be provided by the Evaluation Team in the ‘Inception Report’.

## Evaluation Questions per Criteria

This independent evaluation will enable government and stakeholders to get answers to the following questions. It will contribute to the understanding of key drivers and challenges to the achievement of SDG-4 and targets at the national and sub-national levels.

Table 3: Evaluation questions per criteria

| Evaluation Criteria | Evaluation Questions |
| --- | --- |
| Relevance/ Appropriateness | - R1: Are overall Education Sector policies, strategies in coherence with SDG-4? Is SDG-4 well mainstreamed into Education Sector Strategic Plan 2016-2019? - R2: What is the added value of SDG4 for Education Sector Strategic Plan? |
| Effectiveness | - Ef1: What is the state of SDG-4 in Nigeria in the light of indicators? What and How much progress have been made towards achieving Expected results of Education Strategic Plan 2016-2019 regarding Outputs and Outcomes of the Plan and targets of indicators? - Ef2: What are the key issues that should be addressed in sustainable development policy and strategy? - Ef3: To what extent were the strategies and tools used in the implementation of the programmes able to achieve expected outcomes? - Ef4: To what extent did following Flagship Policies and Programmes of Education Sector achieve overall expected results: Homegrown School Feeding Programme, Social Cash Assistance to poorest families, etc.? |
| Efficiency | - Ec1: What are the Means in place of roll out of SDG-4, target 1? - Ec2: How timely was the mobilization/availability of human and financial resources for the implementation of the strategic programme? - Ec3: How timely were procurement and distribution of pupil learning materials implemented? to what extent has access to learning materials been scaled up? - Ec4: What are Value for Money (Cost effectiveness) of interventions? |
| Impact | - I1: To what extent were the expected changes in pupil’s access & quality of learning achieved (Impact and Outcome)? - the increase of net enrollment ratio per key group of state - the extent to which completion rate at primary education have been improved; - the extent to which progress have been made in reduction of out of school children and improving girls’ education? - I2: What are unintended impact that happened in communities or institutional system? - I3: Causality: Are there any challenges in achieving the key strategic objectives? What are the challenges and strengths? - I4: What are the main driver’s factors of good increased of completion rate at primary school during the 2011-2013 for learning; What are the driver factors of decreasing of primary school completion rate happened in the recent 6 years period 2013-2018 – Bottlenecks Determinants Analysis |
| Human Rights & ‘Leave no one behind’ | - HR1: How are the human rights-based approach and the ‘Leave no one behind’ thinking of Agenda 2030 realized in Nigeria for Universal Basic Education? - HR2: To what extent was the human rights-based approach integrated into Education Sector Programming within Key Flagship Programme design and implementation? |
| Sustainability | S1: To what extend effective systematic Participation of all stakeholders (individuals, communities, Local institutions, States and federal stakeholders) in design, implementation, financing and M&E of Education’s Sector Programmes is functioning to sustain the gains made in achieving Impact, Outcomes and Outputs? |
| Gender Equality | GE1: To what extent Education Sector Strategic Plan and flagship programmes incorporated considerations of gender equality and the empowerment of women and girls into the design, implementation and monitoring of interventions? |
| Equity | - Eq1: To what extent did the programme target the poorest and helped reduce inequalities between the wealthier groups and the poorest groups? - Eq2: To what extent were the barriers (and their causes) to access basic services in the Education in the targeted LGAs, identified and addressed as part of the overall Programme strategy priorities? |
| Universality | Us1: To what extent all child rights for fully integrated universal Education package of services are available and benefiting to children and mothers? |

# Methodology of the Evaluation

## Overview of the Evaluation Design

The complexity of this first global initiative of evaluating SDGs (high level strategic focus) requires a creative thinking and innovative design that will combine mixed methods and approaches that will enable the generation of credible evidence for objective evaluation of the effectiveness and impact of SDG-4 implementation in Nigeria. The evaluation of SDGs is uncommon compared to the usual evaluation of projects and programmes. The design and methodological approach could be a ‘mix’ of theory-based, quantitative/qualitative, quasi-experimental in relation to the set-out evaluation criteria & questions.

Given the multi-faceted nature of the evaluation questions, the use of mixed-methods is recommended. While the use of quantitative methods (e.g., the conduct of an end-line survey and the analysis of secondary household survey data, such as household surveys conducted by national government and statistics office) will provide an insight on the magnitude of the change attributable to the Education Strategic Plan 2016-2019, the use of qualitative methods will enable in-depth understanding of contextual factors that most have influenced the implementation processes and the target populations’ response to the different interventions.

## Recap of available evidence

This independent evaluation will capitalize on existing data, evaluations, studies, researches and monitoring systems from national institutions, development actors and academic institutions. Some of these existing evidence will be used for trend analysis and for the triangulation with primary Household (HH) data to be collected during the evaluation.

Key reference sources of available accurate data and evidence that will be used for assessing trends of impact and outcomes indicators of Theory of Change (ToC) are as follow:

- Education Policies, Strategies and Programme Documents;

- The Implementation Status Report 2016-2018 on Education For Change (Education Sector Strategic Plan)

- Annual Education Statistical Report (Education Census) – EMIS Report

- Annual Performance Monitoring Progress Report of Flagship programmes;

- MICS 2011; MICS 2016-2017; NDHS 2018

- SDGs Baseline Indicators Report 2016; and Nigeria VNR Report 2017

- HIV-AIDS HH Survey 2018

- Nigerian Living Standard Survey (NLSS) 2018-2019

- Geo-Reference Infrastructure and Development Survey (GRID3) (MBNP)

- Studies and researches completed in Education thematic areas.

Summary synthesis of key relevant studies, researches and evaluations completed for Health Sector during the last 10 years will be undertaken and serve as key evidence support documents to the independent evaluation.

## Quasi Experimental Design

With respect to the impact evaluation questions, a Quasi-Experimental Design (QED) will be used. SDG principles of Universality, Equity, ‘Leave no one behind’ impose to assess geographic inequality of universal basic education by State and to assess why some States are lagging behind SDG-4.1. Geographic disparity in Completion Rate shows a big gap of low performance in Sokoto State (Completion Rate of 18.7% - about 5.3 times below SDG-4 target of 100%) in comparison to a very high completion rate of 115.6% in Delta state.

The QED approach will consider the assessment of merit of Education Sector Strategic Plan and their flagship programmes in the following Six (6) selected States with application of statistical comparison analysis of differences:

- Two (2) High performing states in terms of school completion rate and the achievement of SDG-4.1 in Nigeria (very high CR): Delta State (CR of 115.6% – SDG4 already achieved) and Kwara State (CR of 95.2%); Kwara state is an interesting case for learning of success of human development in combining both achieved SDG 3 (low U5MR) and achieving SDG4.

- Two (2) Transiting states (transiting from bad to good and vice versa) toward SDG4: Katsina State (CR of 65.5%) and Enugu State (CR of 65.4%);

- Two (2) Low performing states in terms of school completion rate and the achievement of SDG-4.1 – Very Low level of Completion Rate: Sokoto State (CR of 18.7%) and Kebbi State (CR of 34.3%).

The geo-ecologic/climatic, political and economic/public financing context of those three  categories of states provide interesting contexts for comparative trend analysis of impact and  outcome indicators from HH Surveys and in-depth causal analysis and determinants of drivers of success and shortfalls for better understanding of why the differences between states in the achievement of SDG-4. These will provide useful learning across the states. For example, what makes significant difference between Delta and Kwara states with Sokoto and Kebbi states vis-à-vis SDG4, in relation to access and quality basic education? Are contextual differences, such as demographic dividend, economic growth, insecurity, public financing (GDP per capita for education), human capital, governance, social norms and family behavior responsible for this? Or are these variations caused by inequality and availability/access to high impact social services?

Figures 4 and 5 summarize the overview of inequity in SDG-4 states that serves as selection criteria of those 6 states for the application of Quasi-Experiment Design approach in assessing the Impact and generating solid evidence and explanations. Four types of quantitative data sources and analysis will be performed:

Four types of quantitative data sources and analysis will be performed:

- Secondary data analysis of existing Nationwide Household Survey: NDHS 2018, MICS 2016-2017; MICS 2011 etc.

- Trends Secondary data analysis of Education Census from 2010 to 2019 in Selected comparison group states;

- Completion of primary quantitative data collection through representative Household Survey in Sampling of LGAs, Communities and 1,000 Sample of HH per State (total sampling of 6,000 Household for 6 States); Indicators from HH surveys will focus on impact & outcomes and services coverage of access and quality of basic education + WASH indicators for evidence on Impact Evaluation’s Criteria;

- Analysis of Routine Administrative Data of EMIS, WASH MIS, etc.

- Monitoring Data: both on Resources and Programme Management.

Figure 4: Four levels of comparative analysis will be done for each of 6 states with reference to TOC:

IMPACT

OUTCOMES

OUTPUTS

Bottlenecks/Determinants Analysis: i) Enabling Environment, ii) Supply, iii) Demand, iv) Quality of Services using UNICEF’s Equity Determinants Analysis Framework (MORES).

Detailed Methodology and Sampling method of calculation and selection of the Quantitative Primary Household Data collection will be developed and submitted within the Evaluation Inception Report by the bidders/Consult Firm for review by the Technical Working Group on SDGs Evaluation (TWG-SDGEVAL) and the National Steering Committee (NSC).

Table 4: Comparison group of three (3) categories of States based on Completion Rate is-à-vis SDG-4 Target (100%).

| Very Low Level of Completion Rate at Primary School |  | Medium Level of Completion Rate |  | Very High Level of Completion Rate |  |
| --- | --- | --- | --- | --- | --- |
| Worst Situation of States Very Far vis-à-vis SDG4-Completion Rate Target of 100% in 2030 |  | Intermediate Status of States vis-à-vis SDG4-CR Target of 100% in 2030 |  | Better Status of States very close to achieve SDG4-Completion Rate of 100% in 2030 (Best Model of Performing States /Treatment Group for Learning of WHY/HOW) |  |
| Name of State | Completion Rate | Name of State | Completion Rate | Name of State | Completion Rate % |
| Sokoto | 18.7 | Benue | 55.9 | Delta | 115.6 |
| Kebbi | 34.3 | Adamawa | 56.3 | FCT-Abuja | 98 |
| Yobe | 41.8 | Kano | 56.9 | Kwara | 95.2 |
| Gombe | 43.7 | Borno | 57.4 | Taraba | 89.9 |
| Oyo | 47.1 | Niger | 59.0 | Imo | 86.4 |
| Zamfara | 47.9 | Anambra | 59.6 | Rivers | 85.2 |
| Bauchi | 50.7 | Cross River | 59.7 | Akwa Ibom | 83.5 |
|  |  | Nigeria | 63.0 | Plateau | 83.0 |
|  | 34.3 | Ondo | 63.1 | Kogi | 82.2 |
|  |  | Lagos | 63.7 | Nasarawa | 81.5 |
|  |  | Ekiti | 64.9 |  |  |
|  |  | Enugu | 65.4 |  |  |
|  |  | Katsina | 65.5 |  |  |
|  |  | Osun | 67.5 |  |  |
|  |  | Ebonyi | 67.8 |  |  |
|  |  | Jigawa | 68.3 |  |  |
|  |  | Edo | 70.4 |  |  |
|  |  | Ogun | 71.8 |  |  |
|  |  | Bayelsa | 74.2 |  |  |
|  |  | Abia | 74.3 |  |  |
|  |  | Kaduna | 79.0 |  |  |

The successful Consultancy Firm will explore the feasibility to consider combining Propensity Score Matching (PSM) with Difference-in Difference (DID) analysis among the three (3) groups of states, using Primary HH Survey Data. Some alternative or complementary innovative techniques could also be used, including Attribution Analysis and Qualitative comparative analysis.

2 States Champion achieved SDG3

2 Urban States in intermediate SDG3

Key References sources of the Quasi Experiment Design and Impact Measurements are as below – Consulting Team will read for better application:

- the UNICEF Impact Evaluation Methodological Brief No. 8 on “Quasi-Experimental Design and Methods” by Howard White and Shagun Sabarwa;

- the 2012 DFID Working Paper Series on “Broadening the range of designs and methods for Impact Evaluation”15 by Stern et al; and

- the UNICEF Impact Evaluation Methodological Brief No. 9 on “Comparative Case Studies” by Delwyin Goodrick.

## Qualitative methods

Qualitative information will be collected through the following methods:

- Programme document review: this would include an in-depth analysis of programmes progress reports, studies, surveys and past evaluation produced for the Health Sector;

- Summary synthesis of key relevant studies, researches and evaluations completed for the Nigerian Health Sector during the last 10 years will be undertaken and serve as key support documents for the independent SDGs evaluation;

- Semi-structured interviews with the staff of institutions and organizational partners of Health Sector (Health Development Partners Group), with the required programme’s institutional memory and who are, for the most part, still available. Partners include, government agencies, NGOs, and the Donors. UNICEF can help provide a list of key informants and institutions, based on research criteria recommended by the Evaluation Team.

- Focus Group Discussions (FGDs) will be undertaken at community level during the HH Survey with key beneficiaries of health services: Mothers, Adolescents, Village Health Workers and Community leaders, as well as religious groups.

- Direct observations: Visits to selected communities will provide more specific evidence and answers to the evaluation questions.

Detailed methodology for sampling of FGDs and targets participants will be developed and submit by the consultant team.

## Other methodological considerations

Taking into consideration the principle of equity, the design and specific methodology put forward by the Consulting Firm will need to reflect the aspect of equity-focused results. Therefore, next to the measurement of the average effect size of health interventions, some strategies (e.g. equity-based sampling) will need to be included in the suggested methodology so as to capture the impact of the Flagship Policies/Programmes among marginalized households and communities, whose experience and response to the program may not be fully captured by random sampling.

## Data Processing & Analysis

As this evaluation design is using a theory-based approach which implies investigating the programme’s Theory of Change and programme logic, the independent evaluation team will analyze both quantitative and qualitative data at the same time to develop a rich analysis of breadth and depth. Applying ‘Contribution Analysis’ provides a structured approach to collecting and reviewing data and developing a ‘contribution story or narrative’. For the collection and analysis of the qualitative data which will require gaining an understanding of changes in knowledge, attitudes and practices, a mixed methods approach is judged as the most appropriate.

### Quantitative data analysis

For the quantitative survey we will be using a ‘quasi-experimental approach. The analysis of data gained from the different surveys to assess what has worked, for whom and in what ways will use Statistical software to manage and carry out data processing, data analysis of determinant factors (applying Multi Variate Regression Analysis) to show intervention effects and using SPSS Software for Regression Analysis of determinants factors of Completion Rate of Basic Education from the HH Surveys or DHS 2018 using adequate Education Conceptual Framework:

- The data from the quantitative survey will be reviewed to assess its contribution to the key questions. Scoring and rating tools will be used to highlight specific examples of data;

- Data will be reviewed to draw out the key issues arising and to look for potential patterns, similarities as well as differences and challenges;

- The findings will be reviewed against other similar studies as well as the literature review;

- The findings will also be used to inform the qualitative field assessment.

### Data Entry, Management and Quality Assurance of HH survey

Field Data collection will be undertaken using new technology (CAPI). The Consulting Firm will apply an electronic data gathering system for the quantitative survey, such that data will be uploaded daily to a ‘secure cloud’, allowing a real-time examination of data quality and daily feedback to the field teams should any problems with the data arise. Analytical quality assurance will be ensured by the presence of Statistical expert among the evaluation team, who will embed QA throughout the design, collection and analysis phases. The Statistician/Data Analyst Expert will also ensure that when the quantitative results are brought alongside the other parts of the analysis that necessary caveats and any assumptions underpinning the applicability and generalizability of the analysis are clear.

### Quality Assurance of data collection for field studies

The evaluation team is structured to ensure a balance of national and international evaluation and health experts. In addition, expertise in gender and social development will be provided by the evaluation team. The field visits will be structured to maximize the opportunities for evaluation team members to gather data and to obtain the perspectives of different stakeholders, especially those who are normally/often overlooked or excluded. All tools will be fully developed prior to field visits and will be tested by the local team.

# SDGs Evaluation Governance & Quality Assurance

The conduct and completion of this independent evaluation of SDG-4 is anchored within the existing institutional governance eco-system of SDGs coordination in Nigeria. The Office of the Senior Special Assistant to the President on SDGs (OSSAP-SDGs) was established at the Presidency to provide leadership and coordinate the planning and implementation of the 2030 Agenda for Sustainable Development and the SDGs in Nigeria. The Senior Special Assistant to the President on SDGs provides overall leadership and guidance at all stages of the SDGs evaluation process, in close coordination with the Ministry of Budget and National Planning, relevant MDAs, and the technical and financial support of the UNICEF Country Representative and Heads of UN Agencies and Development Partners. This high level strategic institutional framework will ensure engagement of line Ministries and partners and lead to the effective utilization of evidence generated by this independent evaluation for adequate policy and strategic measures to accelerate SDGs’ progress in Nigeria.

The Governance eco-system of this Independent SDGs Evaluation in Nigeria is as follows:

## National Steering Committee (NSC) on SDGs Evaluation

The Senior Special Assistant to the President on SDGs (SSAP-SDGs) will set up a National Steering Committee (NSC) on SDG Evaluation. The role of the NSC is to provide strategic leadership and guidance in the conduct and eventual uptake of this independent SDGs evaluation in Nigeria. This includes the provision of political commitment, ownership and high-level technical guidance.

The Main Terms of Reference (ToR) for the National Steering Committee (NSC) on SDGS Evaluation are as follow:

- Ensure adequate visioning, decision making, engagement and buy-in among Governments and development partners, and the eventual uptake of the Independent SDGs evaluation findings by the respective MDAs, UN Agencies and Development Partners to accelerate SDGs progress in Nigeria.

- Review and approve the purpose, scope and the design of the independent evaluation of the three (3) selected SDGs (SDG 1, 3 4) as well as to provide feed-back on the evaluation ToRs.

- Support the selection process for the contracting of the independent evaluation team and their mission in Nigeria, to be managed by UNICEF Nigeria.

- Facilitate all processes of accessing documents and the required agreements for the conduct of the independent SDGs evaluation;

- Review and approve all expected deliverables mentioned in section 8, namely:

  - The Inception Report of the evaluation of each SDG-1, 3 and 4;

  - The Draft1 Final Report after review by the Technical Working Group;

  - The Final High-Quality Copy-edited Report, including Foreword and Photos;

  - One-page summary paper for the attention of His Excellency, the President of Nigeria and a Policy Brief Paper for Policy Advocacy; and key lessons learned for incorporation into the Nigeria VNR Report - 2020.

- Participate in the key meetings with the evaluation team and the launch dissemination of final printed report;

- Provide feedback that can be formally acted upon by the evaluation team;

- Advise on the Management Response/Actions to the Evaluation.

The NSC on SDGs Evaluation will comprise of the following members:

- Hon. Minister of Budget and National Planning (Chairman)

- Hon. Minister of Health

- Hon. Minister of Education

- Hon. Minister of Finance

- Hon. Minister of Women Affairs and Social Development

- Hon. Minister of Youths and Sports Development

- Hon. Minister of Labour and Employment

- Hon. Minister of Agriculture and Rural Development

- Special Adviser to the President, National Social Investment Programme (NSIP)

- Senior Special Assistant to the President on SDGs (SSAP-SDGs) (Secretariat)

- Statistician General of the Federation

- Chairman National Population Commission (NPoPC)

- UNICEF Representative in Nigeria

- UNDP Resident Representative

- DFID Country Director

- Director General SMEDAN

- Private Sector Advisory Group on SDGs (PSAG-SDGs)

- Civil Society: President of Nigerian Association of Evaluators

## Technical Working Group of SDGs Evaluation in Nigeria

In early December 2018, the SSAP-SDGs approved the conduct of an Independent evaluation of priority SDGs in Nigeria in order to ensure evidence-based SDGs reporting via the National Voluntary Review. Nigeria is due to submit its VNR 2020. Thus, to ensure the smooth conduct of this independent evaluation, the SSAP-SDGs established a Technical Working Group on SDGs Evaluation (TWG-SDGEVAL) in Nigeria, in coordination with the Federal Ministry of Budget and National Planning and UNICEF Nigeria. The TWG-SDGEVAL was able to organize the SDGs Evaluation Capacity Building Workshop held in Lagos between February 4-8, 2019. It involved about 45 participants drawn from relevant MDAs and development partner institutions, and aimed to build their capacity on SDGs evaluation and to develop draft Terms of Reference (ToR) for the proposed SDGs evaluation.

The TWG-SDGEVAL has the following ToR:

- To work closely with the NBS during the review and validation of SDGs Indicators as part of the ongoing re-alignment of the National Statistical System with the requirements and indicators of the SDGs.

- To identify and recommend 1-3 priority SDGs for UNICEF-funded Independent Impact Evaluation that will strengthen Nigeria’s 2020 NVR report.

- Work with and mobilize other stakeholders and partners in support of evaluation and reporting of the SDGs in Nigeria.

The TWG-SDGEVAL has the following members:

- Dr. Lawal Zakari - Director, National Monitoring and Evaluation at MBNP, Chair of the TWG-SDGEVAL

- Dr. Robert Ndamobissi - Evaluation Manager, UNICEF

- Engr. Ahmad Kawu - Director, Monitoring and Evaluation, OSSAP-SDGs

- Dr. Bala Yunusa - Senior Technical Advisor, OSSAP-SDGs

- Dr. Ify Ukaegbu - Education/Special Assistant on Programmes, OSSAP-SDGs

- Rose Keffas - Special Assistant MDAs, OSSAP-SDGs.

- Representative of the National Bureau of Statistics (NBS)

The Technical Working Group will guarantee adequate design and the coordination of the operationalization of the SDGs evaluation and will play critical role in Quality Assurance of deliverables submitted by the Independent SDGs evaluation team before submission to the National Steering Committee (NSC) for review and approval. The TWG-SDGEVAL will ensure the organization of all meetings, workshops and dissemination.

## Timely Management of the Evaluation

This independent SDGs evaluation will be managed directly on a daily basis by the UNICEF’s Evaluation Manager, in inter actions with Section Chief of Education at UNICEF and in close liaison with the Office of Senior Special Assistant to the President on SDGs (OSSAP-SDGs), the Director of Monitoring and Evaluation at the Ministry of Budget and National Planning and the Director of Monitoring & Evaluation at the Federal Ministry of Education and relevant MDAs.

Key management actions will include:

- Co-lead with the Office of the Senior Special Assistant to the President on SDGs (OSSAP-SDGs) and the Federal Ministry of Budget of National Planning, the coordination of all stages of the independent SDGs evaluation in Nigeria, leveraging partnerships with UN agencies, Development Partners, Academia, Nigeria Evaluation Association, nationally and internationally.

- Ensure adequate guidance and facilitation support to TWG-SDGEVAL and NSC on SDGs evaluation in Nigeria.

- Lead on UNICEF’s internal contracting process for the engagement of Consulting Firm in direct collaboration with UNICEF’s Supply Section/Operations,

- Organize and facilitate the inception and all meetings between the Evaluation Team and the TWG-SDGEVAL and the NSC.

- Organize and facilitate Conference calls with the evaluation team where necessary.

- Be the main Focal Point for all communications with the Evaluation Team and with the NSC.

- Facilitate the communication and coordination between the Evaluation Team and various stakeholders.

- Provide strong technical quality assurance on all evaluation design, tools and documents (including key deliverables and interim products) in order to ensure high quality compliance with universal standards of evaluation, defined by UN Agencies (UNEG and UNIEF) in inter actions with the TWG-SDGEVAL. To play critical role of technical guidance to Evaluation Team and review and feed-back the Evaluation team on Drafts documents for revision/improvement until it meets comfortable level of improved quality in respect of evaluation norms of quality before submission to the NSC.

- Support the dissemination of the evaluation findings and strategic debate and the implementation of the management response.

- Support the development of Policy Brief Paper and the insertion of key conclusions and lessons learned into the Nigeria VNR Report 2020.

## Independent Evaluation Consulting Firm Team

The independent evaluation team will be responsible for conducting the SDGs evaluation as described in the Terms of Reference (ToR) and in their detailed proposal. The Evaluation Team Leader, more specifically, will oversee the following:

- Oversight and management of team members.

- Focal Point for all communications with UNICEF Nigeria.

- Orientation and training of team members, and enumerators where applicable.

- Responsible for meeting deadlines and quality of all evaluation products and deliverables.

- Principal author of the Final Report and Policy Brief Paper.

## Oversight Quality Assurance of SDGs Evaluation

In addition to country led responsibility in managing the SDGs evaluation, an oversight Quality Assurance Review system of SDGs Evaluation Design and Report will be implemented systematically using the following external capacities:

  - UNICEF Regional Evaluation Adviser for West and Central African Countries, based in Dakar, Senegal.

  - Independent credible Institute of Evaluation, based in Canada – Universalia - using the existing Service Contract between UNICEF & Universalia for the Quality Review of Evaluation and Research Papers funded by UNICEF Nigeria.

  - UNICEF Director of Independent Evaluation Office, based at HQ in New York, for the global review feed-back comments and endorsement of quality of ToRs, Inception Report, and Final Evaluation Report.

  - DFID Office of Quality Assurance based in UK.

As Nigeria is the first country in the global South to commenced the process of an Independent SDGs evaluation (all other countries are learning from Nigeria), the TWG-SDGEVAL in Nigeria will explore opportunities for knowledge sharing and getting contributions from the global International Organization for Cooperation in Evaluation (IOCE). Others include the African Evaluation Association (AfEA) in the area of oversight and quality assurance of SDG evaluation in Nigeria. This entails building strong country case for replication by other countries and influencing the development of missing global guidance of SDGs evaluation globally.

# Evaluation Expected Deliverables-Outputs

Following are the key expected results that will be produced by the Independent Evaluation Team and submit to UNICEF, OSSAP-SDGs, MBNP and the National Steering Committee (NSC) for review and validation:

- Summary synthesis of existing studies, researches, Assessments, evaluations on Health sector.

- Evaluation of SDG-4 Education Detailed Inception Report.

- Preliminary Findings – PowerPoint presentation at Stakeholders Workshops.

- Draft0 Final Analytical Full Report reviewed and commented by the TWG-SDGEVAL.

- Draft1 Final Analytical Full Report revised and submitted to NSC.

- Draft2 Revised Final Analytical Report submitted to UNICEF & OSSAP-SDGs for approval.

- PowerPoint presentation to the Official Launch Dissemination Event of the Hard Copy Quality Edited Print Out Report and High Level Policy Strategic Debate; and Minutes of Strategic debate and Actions Points from the Official Dissemination.

- High Quality Copy Edited Policy Brief Paper for Public Advocacy towards Decision Makers + Key messages for insertion into Nigeria VNR Report 2020.

# Evaluation workplan

| Activity | Key deliverable | Deadline |
| --- | --- | --- |
| Phase 1: Inception |  |  |
| Activity 1.1: Remotely initial work: Skype Call (Kick-off meeting) & Sharing key documents in Drop Box | Meeting Minutes | Week 1 (1st week of July 2019) |
| Activity 1.2: Country Visit Inception Meeting with Stakeholders | Minutes of Clear High Demand from Stakeholders useful to develop adequate Inception Report | Week 2 (Mid-July 2019) |
| Activity 1.3: Initial Desk Review of existing evidence; finalization of the evaluation matrix, development of methodology and work plan; development of the data collection material; drafting of the inception report | Summary Synthesis of existing Researches, Studies, evaluations, etc. Draft0 Inception Report submitted to UNICEF, OSSAP-SDGs | Weeks 3-6 (Mid-August) |
| Activity 1.4: National Steering Committee Meeting in Abuja; Review and approval of the final inception report | Final inception report | Weeks 8-10 (end August 2019) |
| Phase 2: Data collection and analysis |  |  |
| Activity 2.1: Elaboration and submission of Ethical Protocol to the MoE Ethics Committee and Finalization of Tools | - Ethical Protocol submitted to Ethics Committee Review/Approval - Final Tools of Data collection | Week 11 (1st week of September) |
| Activity 2.2: Enumerators’ training | Training Curriculum | Week 12 (Mid-Sept) |
| Activity 2.3: Data collection and iterative data analysis | Field Data Collection completed Secondary Data Analysis of existing HH Surveys + Routine Statistics | Weeks 13-16 (1rst Week of October until Mid-November) |
| Activity 2.4: Debriefing meeting right after the end of the field data collection | PPT on preliminary debriefing | Last day of Week 16 |
| Activity 2.5: Data Processing and Data Analysis + Transcription/Analysis of Focus Group Discussions | Statistical Tables Produced and Trend Analysis completed | Weeks 15-18 (End November, 2019) |
| Phase 3: Reporting and communication of results |  |  |
| Activity 3.1: Drafting and submission of the evaluation report, of the summary PowerPoint, of the evaluation key findings/messages | SDG Evaluation TWG-SDGEVAL and review and discussions of key findings and recommendations Draft0 Full Evaluation Report | Weeks 19-20 (Mid-December, 2019) |
| Activity 3.2: National Steering Committee Meeting - Review of the Draft1 SDG3 Evaluation Full Report based on the stakeholders’ feedback and resubmission of the final report |  | Week 20-21 (1st week of January 2020) |
| Activity 3.3: Finalization and Quality-Copy Editing and signature of Foreword of the Final SDG Evaluation Report | Final Quality Copy Edited Report including photos and Foreword signed jointly by UNICEF, OSSAP-SDGs and MBNP | Week 22-23 (February 2020) |
| Activity 3.4: Official Launch dissemination Event in Abuja; Presentation of final report findings, conclusions and recommendations | Meeting of key strategic decision of the official launch | Weeks 24-26 (End March, 2020) |
| Phase 4: Policy Brief Paper and Public Advocacy |  |  |
| Activity 4.1: Summary key messages for inclusion into VNR | Key messages from SDG Evaluation included into Nigeria VNR Report 2020 | March, 2020 |
| Activity 4.2: Elaboration of Policy Brief Paper | High Quality Copy Edited Policy Brief Paper is published | April, 2020 |
| Activity 4.3: Elaboration of Article for international journal | Article developed and submitted to Evaluation Journal | June, 2020 |

# Ethical Considerations

The SDGs evaluation will follow UNICEF guidelines on the ethical participation. In addition, all participants in the evaluation will be fully informed about the nature and purpose of the evaluation and their requested involvement. Only participants who have given their written or verbal consent (documented) will be included in the evaluation. All the documents, including data collection, entry and analysis tools, and all the data developed or collected for this evaluation are the intellectual property of the Government of Nigeria and UNICEF.

The Evaluation team members may not publish or disseminate the Evaluation Report, data collection tools, collected data or any other documents produced from this consultancy without the express permission of, and acknowledgement of UNICEF. The bidders are invited to further analyze aspects of methodological and organizational complexity that might affect the evaluation in general and make it difficult to answer some of the questions in particular, and to explain how they will address them.

The evaluation will require an independent ethical review. A particular attention shall be paid to the avoidance of harm and stress to evaluation participants, especially children and other vulnerable populations; obtaining informed consent/verbal assent from them (except from UNICEF staff, who will be directed to participate if needed); absence of benefit or compensation offered to them; protection of their privacy; confidentiality and anonymity of data collected; security matters and protection protocols both for enumerators and key informants; training of enumerators in ethical issues and on enumeration and communication skills.

# Evaluation Team and responsibilities

The evaluation will be carried out by an institution: credible international consortium or academic institution combined with Nigeria Local research Centre, or similar service provider. The number and profile of the evaluation team members will be proposed by the bidders in such a way that the team size, experience, qualifications, references, mix and complementarity of expertise, availability and level of effort are convincing in terms of proposed work plan’s feasibility. The contracted institution will be responsible for recruiting and training of enumerators. The following is suggested as a guidance:

## Evaluation Team Leader: International

The evaluation team leader should possess the following competencies (experts with multi-skill sets can fill more than one competency):

- Required competencies:

- Strong academic qualifications (a PhD would be desirable) in Education, Policy/Strategy Evaluation, research methodology, international development.

- Demonstrated exceptional technical expertise in high-level and high-quality programme and multi-country evaluations and studies;

- Strong qualifications in statistics and data analysis (both quantitative and qualitative);

- Strong expertise and experience in designing and implementing development programmes in rural areas in Africa;

- In-depth knowledge of the global Education sector and global development context and agenda;

- Excellent writing and language skills in English.

- Considered an advantage:

- Experience in using non-traditional and innovative evaluation methods;

- Good knowledge of UNICEF programming strategies, field work, procedures and organizational culture; note: prior involvement of team members with UNICEF should be declared in the technical proposal in order to work around any possible conflicts of interest;

- Knowledge of additional sectors involved in Education Programming;

- Additional considerations:

- The number and level of effort of the respective senior, intermediate level and junior experts should be appropriate and ensure a high quality and timely evaluation process;

- Track record of collaboration (on a similar or different assignment) will be considered a major advantage;

- A strong commitment to delivering timely and high-quality results, i.e. credible evaluations that are effectively used, is necessary;

- A gender balance in the evaluation team is desirable;

- A copy of a recent evaluation report of which the team has been primary author, should be included as part of the documents of the technical proposal.

## Other Members of the Team

The other members of the team should include at least one national and one international:

- One specialized in Economic Policy for Education;

- One specialized Access to Education;

- One specialized on Quality of Education;

- One Specialized in Quantitative Survey – Statistical Data Analysis.

Regarding academic qualifications, an advanced University degree (Master or PhD) is desirable or long years of experience in relevant work. Solid experience in Evaluation is a key advantage.

# Competitive Contracting Bidding Process

UNICEF will apply it procedure of competitive bidding process of contracting and results based management of Consult Firm for delivery of high quality end products in consultations with Government and Governance body of the SDG evaluation mentioned above.

A Request For Proposal (RFP) will be elaborated by UNICEF Supply Section/Operations for the services contract process. Institutional contract with credible reputed worldwide consortium of evaluation in partnership with Nigeria’s local research/evaluation institution will be the preference for this high demanding evidence generation.

Below criteria for the technical assessment of the technical proposal has been defined by UNICEF Evaluation Manager in consultation with the TWG-SDGEVAL. UNICEF Supply Section/Operation will take care of the criteria of financial assessment of offers from bidders.

UNICEF Supply Section will advertise the RFP (Technical and Financial Proposals) at country level and worldwide using all African and international networks. The RFP will be also communicated to the Nigeria Association of Evaluators, the African Evaluation Association of Evaluators and other Asia, European and American Association of Evaluations.

Criteria for technical review of proposals submitted by institutional consult firm

| Technical Criteria | Technical sub-criteria | Max.Points |
| --- | --- | --- |
| Overall Response | Quality analytical understanding of conceptual & policy framework of SDG and presentation of the Purpose & Expectations of evaluating Education Sector Plan for SDG | 5 |
| Standard Strategy/ Methodology for Evaluation | Design, Methodological Approaches & Analysis Framework are very solid to generate credible evidence and answers to Evaluation Questions, Objectives & Ethics | 35 |
| Consult Firm proposed Team dedicated to this evaluation | Team Leader, Team Members, Expertise & Professional experience & knowledge of key strategic areas of the evaluation’s objectives & criteria | 20 |
| Trusted Organization for high level political complex Evaluation | Evidence of concrete experience of Evaluations completed for high level policy decision makers: evaluation of National Policies, National Development Plan or Strategy, Sector Strategic Plan and familiarity with Africa/Nigeria | 20 |
| Total Maximum Points |  | 80 |

Signatories

Elaborated by:	   					Reviewed & Certified by:

Names:  Dr. Zakari Lawal (Director M&E MBNP) 		Name: Dr. Euphrates Efosi Wose

Dr. Bala Yusuf Yunusa (OSSAP-SDGs)

Title: SDG Evaluation Technical Working Group		Title:  Chief of Education at UNICEF

Signatures: _______________________			Signature: ____________________

Date: _________________________			Date: __________________

Reviewed and Finalized by:                                        Endorsed by:

Name: Dr. Robert Ndamobissi		     		Name: Pernille Ironside

Title:	Evaluation Manager at UNICEF	     		UNICEF Deputy Representative

Signature: _____________________	    		 Signature: ____________________

Date : ________________________	                   		Date : ________________________

Approved by:

Name: Peter Hawkins 	 	           	         Name: Princess Adejoke Orelope-Adefulire

Title: UNICEF Representative in Nigeria               Title: Senior Special Assistant to the President of Nigeria on SDGs

Signature: _________________			Signature: ________________________

Date: _____________________                		Date: ______________________

# Annexes

## A1. Evaluation Framework: link between Criteria, Questions and Data Sources

## A2. References & Bibliographies

Nigeria-Education Sector Strategic Plan 2016-2019 (Introduction)

Tanahashi. (1978). Health service coverage and its evaluation. Bulletin of WHO number 56, pp. 295-303

https://www.unicef-irc.org/publications/pdf/brief_8_quasi-experimentaldesign_eng.pdf

https://www.oecd.org/derec/50399683.pdf

https://www.unicef-irc.org/publications/754-comparative-case-studies-methodological-briefs-impact-evaluation-no-9.html

Mayne J (2008) Contribution Analysis: An approach to exploring cause and effect. ILAC Brief 16 May 2008.

Concept Note of the Technical Working Group of SDG Evaluation in Nigeria

http://www.unicef.org/supply/files/ATTACHMENT_IV-UNICEF_Procedure_for_Ethical_Standards.PDF